## Works Programme
Padma View Specialised Hospital Extension — Works Programme
Project code PVH-2026 · Contract sum ৳ 60,00,00,000 · Revision C, issued 14 September 2026
Task | Parent task | Type | Trade | Assignee | Start | Finish | Cost (BDT) | Priority | Status
Site Preparation & Enabling |  | Phase | General | Shahidul Haque | 2026-02-02 | 2026-03-26 |  | High | Completed
Site hoarding and office setup | Site Preparation & Enabling | Construction | General | Shahidul Haque | 2026-02-02 | 2026-02-19 | 4200000 | High | Completed
Soil test and topographic survey | Site Preparation & Enabling | Survey | General | Kamrul Hasan | 2026-02-09 | 2026-02-26 | 2100000 | High | Completed
Demolition of old block | Site Preparation & Enabling | Construction | Earthworks | Shahidul Haque | 2026-03-01 | 2026-03-26 | 8600000 | High | Completed
Temporary power and water connection | Site Preparation & Enabling | Construction | Electrical | Tanvir Ahmed | 2026-03-01 | 2026-03-19 | 3600000 | Normal | Completed
Piling & Foundation |  | Phase | Piling | Nusrat Jahan | 2026-03-29 | 2026-07-09 |  | High | Completed
Bored piling - 320 piles | Piling & Foundation | Construction | Piling | Nusrat Jahan | 2026-03-29 | 2026-05-21 | 48000000 | High | Completed
Pile caps and grade beams | Piling & Foundation | Construction | Concrete | Nusrat Jahan | 2026-05-24 | 2026-06-25 | 19500000 | High | Completed
Earth filling and compaction | Piling & Foundation | Construction | Earthworks | Farhana Akter | 2026-06-07 | 2026-06-25 | 5400000 | Normal | Completed
Below-ground drainage | Piling & Foundation | Construction | Plumbing | Farhana Akter | 2026-06-14 | 2026-07-09 | 6100000 | Normal | Completed
Superstructure |  | Phase | Concrete | Nusrat Jahan | 2026-07-12 | 2026-12-17 |  | High | In Progress
Level 1 slab casting | Superstructure | Construction | Concrete | Nusrat Jahan | 2026-07-12 | 2026-08-06 | 26500000 | High | Completed
Level 2 slab casting | Superstructure | Construction | Concrete | Nusrat Jahan | 2026-08-09 | 2026-09-03 | 26500000 | High | In Progress
Level 3 slab casting | Superstructure | Construction | Concrete | Nusrat Jahan | 2026-09-06 | 2026-10-01 | 26500000 | High | In Progress
Level 4 slab casting | Superstructure | Construction | Concrete | Nusrat Jahan | 2026-10-04 | 2026-10-29 | 26500000 | High | Open
Level 5 and roof deck | Superstructure | Construction | Concrete | Nusrat Jahan | 2026-11-01 | 2026-12-03 | 28000000 | High | Open
Stair and lift core | Superstructure | Construction | Rebar | Kamrul Hasan | 2026-11-15 | 2026-12-17 | 8000000 | Normal | Open
Envelope & Roofing |  | Phase | Glazing | Sabrina Chowdhury | 2026-08-16 | 2027-02-25 |  | High | In Progress
Glazing sample panel approval | Envelope & Roofing | Design | Glazing | Sabrina Chowdhury | 2026-08-16 | 2026-09-05 | 1500000 | Urgent | Blocked
External masonry and plaster | Envelope & Roofing | Construction | Masonry | Sabrina Chowdhury | 2026-10-11 | 2026-12-24 | 24000000 | High | Open
Aluminium glazing installation | Envelope & Roofing | Construction | Glazing | Sabrina Chowdhury | 2026-12-06 | 2027-02-25 | 27000000 | High | Open
Roof waterproofing | Envelope & Roofing | Construction | General | Farhana Akter | 2026-12-20 | 2027-01-28 | 7500000 | High | Open
External painting | Envelope & Roofing | Construction | Painting | Farhana Akter | 2027-01-31 | 2027-02-25 | 4000000 | Normal | Open
MEP Installation |  | Phase | HVAC | Tanvir Ahmed | 2026-11-01 | 2027-04-15 |  | High | Open
Electrical first fix | MEP Installation | Construction | Electrical | Tanvir Ahmed | 2026-11-01 | 2027-01-14 | 22000000 | High | Open
Plumbing first fix | MEP Installation | Construction | Plumbing | Tanvir Ahmed | 2026-11-15 | 2027-01-28 | 16500000 | High | Open
HVAC ducting and chillers | MEP Installation | Construction | HVAC | Tanvir Ahmed | 2027-01-03 | 2027-03-11 | 26000000 | High | Open
Generator and substation | MEP Installation | Construction | Electrical | Tanvir Ahmed | 2027-01-24 | 2027-03-25 | 19500000 | High | Open
Fire protection system | MEP Installation | Construction | Fire Safety | Tanvir Ahmed | 2027-02-14 | 2027-04-15 | 12000000 | High | Open
Internal Finishing |  | Phase | Tiling | Imtiaz Rahman | 2027-01-03 | 2027-05-13 |  | High | Open
Internal masonry and plaster | Internal Finishing | Construction | Masonry | Imtiaz Rahman | 2027-01-03 | 2027-02-18 | 18000000 | High | Open
Floor tiles and marble | Internal Finishing | Construction | Tiling | Imtiaz Rahman | 2027-02-21 | 2027-04-08 | 24000000 | High | Open
Doors and joinery | Internal Finishing | Construction | General | Imtiaz Rahman | 2027-03-14 | 2027-04-22 | 15500000 | Normal | Open
Operation theatre fit-out | Internal Finishing | Construction | HVAC | Tanvir Ahmed | 2027-03-07 | 2027-04-29 | 18000000 | Urgent | Open
Painting and finishing | Internal Finishing | Construction | Painting | Imtiaz Rahman | 2027-04-11 | 2027-05-13 | 5500000 | Normal | Open
Commissioning & Handover |  | Phase | General | Md. Rafiqul Islam | 2027-03-21 | 2027-06-30 |  | High | Open
Lift installation and testing | Commissioning & Handover | Construction | Lifts | Tanvir Ahmed | 2027-03-21 | 2027-05-06 | 14000000 | High | Open
External works and landscaping | Commissioning & Handover | Construction | Earthworks | Farhana Akter | 2027-04-04 | 2027-05-27 | 6500000 | Normal | Open
Systems commissioning | Commissioning & Handover | Commissioning | HVAC | Tanvir Ahmed | 2027-05-16 | 2027-06-17 | 6000000 | High | Open
Handover documents and training | Commissioning & Handover | Handover | General | Md. Rafiqul Islam | 2027-06-06 | 2027-06-30 | 2500000 | Normal | Open
Total (tasks)