## Procurement
Padma View Specialised Hospital Extension — Procurement Schedule
Items still marked Requested whose need-by date falls inside the lead time require immediate action.
Item | Supplier | Trade | Quantity | Unit | Unit cost (BDT) | Status | Needed by | Ordered on | Notes | Line total (BDT)
Aluminium glazing units | Brahmaputra Glass Ltd | Glazing | 1850 | sft | 3400 | Requested | 2026-12-06 |  | 12-week lead time from sample approval. Sample not yet approved. | 6290000
Passenger and stretcher lifts - 4 no. | Dhaleshwari Lift Company | Lifts | 4 | unit | 3200000 | Requested | 2027-03-21 |  | Imported, 16-week lead time. Order-by date has passed. | 12800000
HVAC chiller units - 2 no. | Surma Air Systems | HVAC | 2 | unit | 8600000 | Ordered | 2027-01-03 | 2026-08-11 | Factory acceptance test report required. | 17200000
Diesel generator 600 kVA | Karnaphuli Electricals | Electrical | 1 | unit | 7800000 | Ordered | 2027-01-24 | 2026-09-01 | Soundproof canopy included. | 7800000
MS rod, Grade 60 | Turag Steel Industries | Rebar | 420 | ton | 92000 | Ordered | 2026-10-04 | 2026-08-24 | For Levels 4 and 5. | 38640000
Portland composite cement | Shitalakshya Cement | Concrete | 9600 | bag | 560 | Ordered | 2026-10-04 | 2026-09-07 |  | 5376000
Vitrified floor tiles | Teesta Tiles Ltd | Tiling | 42000 | sft | 185 | Quoted | 2027-02-21 |  | Anti-bacterial grade for the operation theatres. | 7770000
Fire hydrant and sprinkler system | Rupsha Building Products | Fire Safety | 1 | package | 9400000 | Quoted | 2027-02-14 |  | Fire Service and Civil Defence approval required. | 9400000